## Read Me
Pre-Production (PP) Meeting & Approval Checklist
Free template by Eco Jersey • ecojersey.com • Custom apparel manufacturing
What this checklist does
The PP meeting is the final sign-off before bulk production starts. This workbook walks the buyer, merchandiser and factory through every element of the order — fabric, trims, sample, decoration, measurements, packaging, planning and compliance — and records each approval. Choose a status for every check and the workbook tells you whether you are cleared to start bulk.
Work through the tabs in order
1. Meeting Info | Enter the order and meeting details and the attendees. The headline readiness verdict appears here automatically.
2. Approval Checklist | The core sign-off. For every item, pick a status (Approved, Pending, Not approved, N/A) and note who is responsible, the date and any remarks.
3. Risk & Action Log | Capture open issues that must be resolved before or during production, with a severity, an owner and a due date.
4. Dashboard | A readiness summary — approval stats, a go / no-go verdict, approval by category, charts, and a sign-off block for signatures.
How the verdict works
CLEARED — every applicable check is approved; bulk can start. CONDITIONAL — some checks are still pending; resolve them before or at bulk start. NOT CLEARED — at least one check is rejected; do not start bulk until it is fixed.
Status colour code
Approved | Green — signed off and ready.
Pending | Amber — awaiting approval or evidence.
Not approved | Red — rejected; blocks bulk start.
N/A | Grey — not applicable to this order.
Good to know
• Mark a check N/A if it does not apply (for example, embroidery on a print-only style) — N/A items are excluded from the readiness score.
• Every open issue in the Risk & Action Log should have an owner and a due date so nothing is forgotten once production begins.
• Keep the signed-off sample sealed and at the factory as the production reference.
• This is a planning and record-keeping tool — confirm all approvals with your manufacturer.
• Need a production partner or a quote? Visit ecojersey.com or ecojersey.com/request-quotation/

## Meeting Info
PP Meeting Information
Fill the blue cells. The readiness verdict updates from the Approval Checklist.
Order & meeting details
Brand / Buyer | Your Brand Name
Style name | e.g. Classic Pullover Hoodie
Style number | EJ-001
PO number | PO-1001
Order quantity (pcs) | 500
Meeting date | 2026-06-15
Planned bulk start | 2026-06-25
Meeting location / mode | Factory / Zoom
Readiness verdict
Status | CONDITIONAL | Resolve pending items before or at bulk start.
Readiness | 84.38% | Approved as a share of applicable checks
Attendees
Name | Role | Company | Present
Buyer / Brand rep
Merchandiser
Production / Factory head
QA / QC head

## Approval Checklist
Pre-Production Approval Checklist
Pick a status for every item. Approved or N/A = cleared. Pending or Not approved must be resolved.
Checklist item | Status | Responsible | Date | Remarks
Fabric & material
Bulk fabric shade & hand-feel approved | Approved | Buyer | 2026-06-15 | Matches approved swatch
Lab dips / shade bands approved | Approved | Buyer | 2026-06-15
Fabric test report received (shrinkage, GSM, colourfastness) | Pending | QA | 2026-06-22 | Awaiting mill report
Bulk fabric quantity confirmed in-house | Approved | Factory | 2026-06-15
Knitting / weaving quality approved | Approved | QA | 2026-06-15
Trims & accessories
All trims approved (zips, buttons, drawcords, eyelets) | Approved | Buyer | 2026-06-15
Labels approved (main, care, size) | Approved | Buyer | 2026-06-15
Hangtags & packaging trims approved | Pending | Merchandiser | 2026-06-22 | Final artwork pending
Sewing thread shade matched | Approved | Factory | 2026-06-15
Trim quantity confirmed in-house | Approved | Factory | 2026-06-15
Sample & fit
PP sample approved | Approved | Buyer | 2026-06-15 | Sealed sample issued
Fit / size-set approved | Approved | Buyer | 2026-06-15
Construction & workmanship approved | Approved | QA | 2026-06-15
Tech pack / measurement spec finalised | Approved | Merchandiser | 2026-06-15
Sealed approved sample at factory | Approved | Factory | 2026-06-15
Print / embroidery / decoration
Artwork / strike-off approved | Approved | Buyer | 2026-06-15
Print placement & dimensions confirmed | Approved | Merchandiser | 2026-06-15
Print wash / rub-fastness test passed | Pending | QA | 2026-06-22 | Re-test after ink change
Embroidery sample approved | N/A |  |  | Print-only style
Measurements & grading
Size chart / grading approved | Approved | Merchandiser | 2026-06-15
Measurement tolerance agreed | Approved | QA | 2026-06-15 | +/- per spec
Marker / consumption confirmed | Approved | Factory | 2026-06-15
Packaging & shipping
Packing method & ratio confirmed | Approved | Merchandiser | 2026-06-15
Carton markings / shipping marks approved | Pending | Buyer | 2026-06-22 | Awaiting final marks
Folding & polybag approved | Approved | Factory | 2026-06-15
Assortment / size ratio confirmed | Approved | Merchandiser | 2026-06-15
Production planning
Production schedule agreed | Approved | Factory | 2026-06-15
Line plan / capacity confirmed | Approved | Factory | 2026-06-15
Order quantity & size ratio confirmed | Approved | Merchandiser | 2026-06-15
Delivery / ship date confirmed | Approved | Buyer | 2026-06-15
Compliance & QC
AQL inspection level agreed (e.g. 2.5) | Approved | QA | 2026-06-15
Needle / metal detection policy confirmed | Approved | QA | 2026-06-15
Social / technical compliance confirmed | N/A |  |  | Not required this order
Required certifications confirmed (OEKO-TEX etc.) | Pending | Buyer | 2026-06-22 | Certificate copy awaited

## Risk & Action Log
Risk & Action Log
Track open issues that must be resolved before or during production.
# | Issue / risk | Category | Severity | Owner | Raised | Due date | Status | Resolution / action
1 | Fabric test report awaited from mill | Fabric | High | QA | 2026-06-12 | 2026-06-20 | Open | Chase mill; hold cutting until received
2 | Hangtag artwork pending final buyer sign-off | Trims | Medium | Merchandiser | 2026-06-14 | 2026-06-21 | Open | Buyer to approve revised artwork
3 | Print rub-fastness re-test after ink change | Decoration | Medium | QA | 2026-06-13 | 2026-06-22 | In progress | Lab test booked
4 | OEKO-TEX certificate copy to be provided | Compliance | Low | Buyer | 2026-06-15 | 2026-06-25 | Open | Supplier to send PDF
5
6
7
8
9
10
11
12

## Dashboard
PP Readiness Dashboard
Live sign-off summary — updates from the checklist and risk log.
Go / no-go verdict |  | Readiness |  | Open risks
CONDITIONAL |  | 84.38% |  | 4
Approved |  | Pending |  | Not approved
27 |  | 5 |  | 0
Applicable checks |  | Marked N/A |  | High-severity open
32 |  | 2 |  | 1
Status breakdown |  |  | Approval by category
Status | Count |  | Category | Approved | % approved
Approved | 27 |  | Fabric & material | 4 | 80%
Pending | 5 |  | Trims & accessories | 4 | 80%
Not approved | 0 |  | Sample & fit | 5 | 100%
N/A | 2 |  | Print / embroidery / decoration | 2 | 66.67%
|  |  | Measurements & grading | 3 | 100%
|  |  | Packaging & shipping | 3 | 75%
|  |  | Production planning | 4 | 100%
|  |  | Compliance & QC | 2 | 66.67%
Sign-off
Role | Name |  | Signature |  | Date
Buyer / Brand
Merchandiser
Production / Factory
QA / QC
Eco Jersey — custom apparel manufacturing • ecojersey.com • Request a quote: ecojersey.com/request-quotation/